## PIEDMONT WATER WW PROGRAM
PIEDMONT WATER-WASTEWATER PROGRAM 2025-2027
OWRB LOAN | FAP-25-0001-L | 21879317.15 |  |  | AVL FUNDS | 21167528.15 | AFTER CLOSING
PROJECT # | CLIENT | PROJECT NAME/DESCRIPTION | TARGET BID DATE | PROGRAM BUDGET | ENGR MANG | CA LEAD | CM INSP | SUB | QC
| CITY OF PIEDMONT | LOAN PROCEEDS/CLOSING COST | 2025-02-01 | 711789 |  |  |  | MFS/PFL | JW/JS
PMA 25-001 | CITY OF PIEDMONT | DISTRIBUTION IMPROVEMENTS SYSTEM WIDE | 2025-03-25 | [5 empty] | PWORKS
PMA 25-002 | CITY OF PIEDMONT | 1 MG TANK | 2025-07-25 | [5 empty] | PWORKS
PMA 25-003 | CITY OF PIEDMONT | WATER WELL IMPROVEMENTS | 2025-10-25 | [5 empty] | PWORKS
PMA 25-004 | CITY OF PIEDMONT | SECONDARY OKC CONNECTION/POLICY 1A OKC AGREEMENT | 2025-11-01 | [5 empty] | PWORKS
PMA 25-005 | CITY OF PIEDMONT | WATERLINE IMPROVEMENTS & PUMP STATION | 2026-01-26 |  | 0 |  |  |  | PWORKS
PMA 25-006 | CITY OF PIEDMONT | SSES PROGRAM (APRIL TO OCTOBER 2025) | 2025-04-25 | [5 empty] | PWORKS
PMA 25-007 | CITY OF PIEDMONT | WASTWATER MASTER PLAN (APRIL TO NOV 2025) | 2025-10-25 | [5 empty] | PWORKS
PMA 25-008 | CITY OF PIEDMONT | WW LIFT STATION AND INTERCEPTOR IMPROVEMENTS | 2026-03-01 |  | 0 |  |  |  | PWORKS
PMA 25-009 | CITY OF PEIDMONT | EASEMENT AND ROW FUNDS | 2025-04-26
PMA 25-010 | CITY OF PIEDMONT | SYSTEM EQUIPMENT - WATER FY 26 | 2025-07-25
PMA 26-001 | CITY OF PIEDMONT | SYSTEM EQUIPMENT - WATER FY 27 | 2026-07-26
PMA 26-002 | CITY OF PIEDMONT | SYSTEM EQUIPMENT - WASTEWATER FY 27 | 2026-07-01
SRB 117849 TASK 1 | CITY OF PIEDMONT | DISTRIBUTION IMPROVEMENTS SYSTEM WIDE | 2025-03-31 |  | ROBERT MULLINS | CRAIG WALLACE | CS INSP |  | CW/CS INSP
SRB 117849 TASK 2 | CITY OF PIEDMONT | 1 MG TANK | 2025-07-25 |  | ROBERT MULLINS | CRAIG WALLACE | CS INSP |  | CW/CS INSP
SRB 117849 TASK 3 | CITY OF PIEDMONT | WATER WELL IMPROVEMENTS | 2025-10-25 |  | GRADY WADE | CRAIG WALLACE | CS INSP |  | CW/CS INSP
SRB 117849 TASK 4 | CITY OF PIEDMONT | SECONDARY OKC CONNECTION (PMA COST-OKC NOT INCLUDED | 2025-11-01 |  | GRADY WADE | CRAIG WALLACE | CS INSP |  | CW/CS INSP
SRB 117849 TASK 5 | CITY OF PIEDMONT | WATERLINE IMPROVEMENTS & PUMP STATION | 2026-01-26 |  | GRADY WADE | CRAIG WALLACE | CS INSP |  | CW/CS INSP
SRB 117849 TASK 6 | CITY OF PIEDMONT | SSES PROGRAM (APRIL TO OCTOBER 2025) | 2025-04-25 |  | AMANDA WAY |  |  | WOOLPERT | CS INSP
SRB 117849 TASK 7 | CITY OF PIEDMONT | WASTWATER MASTER PLAN (APRIL TO NOV 2025) | 2025-10-25 |  | AMANDA WAY |  |  |  | CS INSP
SRB 117849 TASK 8 | CITY OF PIEDMONT | WW LIFT STATION AND INTERCEPTOR IMPROVEMENTS | 2026-03-01 |  | AMANDA WAY | CRAIG WALLACE | CS INSP |  | CW/CS INSP
|  |  | Total | 711789